## Slide 1: MSCC 2019 Collection Analysis Planning – Minerva Webinars
August 21 & September 7 2018
Matthew Revitt, Maine Shared Collections Librarian
www.maineinfonet.org/mscs/

## Slide 2: Agenda
  Introductions
  Overview of process
  Scope of analysis
  Project timeline
  Next Steps

## Slide 3: Introductions
Matthew Revitt, Maine Shared Collections Librarian
Sara Amato, MSCC Contracted Systems Librarian
Andy Breeding, Consulting Software Engineer, OCLC Sustainable Collection Services
Cynthia Duchane, OCLC Sustainable Collection Services

## Slide 4: Participating Libraries – Founders
  Bangor Public Library
  Bates College
  Bowdoin College
  Colby College
  Maine State Library
  Portland Public Library
  University of Maine Orono
  University of Southern Maine

## Slide 5: Participating Libraries - URSUS
  University of Maine Augusta
  University of Maine Farmington
  University of Maine Fort Kent
  University of Maine Machias
  University of Maine Presque Isle

## Slide 6: Participating Libraries - Minerva
      Edythe L. Dyer PL
      Gardner PL
      Jesup PL
      McArthur PL
      Norway PL
      Old Town PL
      Rice PL
      Scarborough PL
      Southern Maine CC
      St. Joseph’s College
      Thomas Memorial PL
      Unity College
      Wells PL
      Windham PL
      Witherle PL

## Slide 7: Overview of Process
Group collection analysis - print monographs only to identify titles agree will retain for 15 years
Contracted with OCLC Sustainable Collection Services to use online analytics tool GreenGlass
Collections & Operations Committee responsible for analyzing collective collection & agreeing retention rules
Will seek participating libraries feedback on retention rules
MSCC Executive Committee have final sign off on retention model

## Slide 8: Collections & Operations Committee
Joan Campbell, Bowdoin College
Evelyn Greenlaw, University of Southern Maine
Patrick Layne, Bangor Public Library
Jenna Mayotte, Portland Public Library
Ana Noriega, Colby College
Peggy O’Kane, Maine State Library
Deb Rollins, University of Maine, Orono
Krystie Wilfong, Bates College
Kathy Woodside, Jesup Memorial Library

## Slide 9: Executive Committee
Marjorie Hassen, Bowdoin College
David Nutty, University of Southern Maine
Jamie Ritter, Maine State Library
Joyce Rumery, University of Maine
Ben Treat, Bangor Public Library

## Slide 10: Scope of Analysis
In Scope:
  Circulating print monographs, pub or acq. 2003-2012
  Juvenile titles (caveats)
Out of Scope
  Monographs with existing MSCC commitments
  Serials (anything with record type ‘s’)
  Micro-formats/Fiche
  Government Documents
  Reference Books
  E-Books
  Music scores
  Lost/Damaged/Withdrawn items
  Special Collections
  Theses/Dissertations
  Maps

## Slide 11: Estimated Bib Record Totals
Library | No. of Monographs
Bangor Public | 55,200
Bates College | 98,900
Bowdoin College | 88,600
Colby College | 86,200
Maine State Library | 30,900
UMaine | 101,000
UMaine Augusta | 14,300
University of Southern Maine | 17,900
University of Maine at Machias | 3,700
University of Maine at Fort Kent | 9,800
University of Maine at Farmington | 13,600
University of Maine at Presque Isle | 2,800
Portland Public Library | 49,400
Minerva | 150,000
Totals | 722,300

## Slide 12: Excluding Specific Publishers from Commitments
Will be excluding from retention consideration specific publishers whose works are temporary in nature e.g. textbooks and travel guides
Collections & Operations Committee working on adding to publishers list, focus on juvenile fiction

## Slide 13: Project Outline
Libraries: Complete OCLC/SCS Cataloging & Data Questionnaire
SCS: Data validation & holdings lookups
SCS: Compile and Validate Individual Data Summaries
Libraries: Provide Bibliographic, Item, Circulation Data

## Slide 14: Project Outline cont.…
SCS: Compile data into GreenGlass/kick-off Collections & Operations Committee meeting to review
SCS: Allocate Retention Commitments
SCS: Reload GreenGlass Data to Reflect Retentions
Collections & Operations Committee: Meetings to experiment & agree on retention rules

## Slide 15: Project Outline cont.…
Libraries: Review Retention Proposals & rejected allocations reported to SCS
Load retention commitments into Sierra
SCS: GreenGlass reloaded with FINAL retention commitments

## Slide 16: Timeline
Starting data questionnaires & submissions (January/February 2019)
Collections & Operations Committee meet to agree on retention rules (May-July 2019)
Retention commitment review (July-August 2019)
Load agreed retention commitments into local ILSs & OCLC WorldCat (September-October 2019)
Does this proposed schedule work?

## Slide 17: Expectations for your Libraries
Provide the information needed to extract the holdings data for the analysis
Feedback on a set of proposed retention rules
Review a list of titles your library has been allocated

## Slide 18: Next Steps
Send out data questionnaires to libraries – January 2019
Billing libraries – January 2019

## Slide 19
Thanks