## Slide 1: MSCC 2019 Collection Analysis - Planning Meeting
www.maineinfonet.org/mscs/

## Slide 2: Agenda
2019 analysis planning
  Introductions
  Overview of process
  Agree on scope
  Agree timeline
  GreenGlass demo
  Next Steps
  Other Business

## Slide 3: Intros – Collections & Ops Comm.
Joan Campbell, Bowdoin College
Evelyn Greenlaw, University of Southern Maine
Patrick Layne, Bangor Public Library
Jenna Mayotte, Portland Public Library
Ana Noriega, Colby College
Peggy O’Kane, Maine State Library
Deb Rollins, University of Maine, Orono
Krystie Wilfong, Bates College
Kathy Woodside, Jesup Memorial Library

## Slide 4: Intros cont..
Matthew Revitt, Maine Shared Collections Librarian
Andy Breeding, Consulting Software Engineer, OCLC Sustainable Collection Services
Cynthia Duchane, OCLC Sustainable Collection Services
Sara Amato, MSCC Contracted Systems Librarian

## Slide 5: Overview of Process
Group collection analysis - print monographs only to identify titles agree will retain for 15 years
Contracted with OCLC Sustainable Collection Services to use online analytics tool GreenGlass
Collections & Operations Committee responsible for analyzing collective collection & agreeing retention rules
Will seek feedback on retention rules from reps at participating libraries
MSCC Executive Committee have final sign off on retention model

## Slide 6: Participating Libraries – Founders
  Bangor Public Library
  Bates College
  Bowdoin College
  Colby College
  Maine State Library
  Portland Public Library
  University of Maine Orono
  University of Southern Maine

## Slide 7: Participating Libraries - URSUS
  University of Maine Augusta
  University of Maine Farmington
  University of Maine Fort Kent
  University of Maine Machias
  University of Maine Presque Isle

## Slide 8: Participating Libraries - Minerva
      Edythe L. Dyer PL
      Gardner PL
      Jesup PL
      McArthur PL
      Norway PL
      Old Town PL
      Rice PL
      Scarborough PL
      Southern Maine CC
      St. Joseph’s College
      Thomas Memorial PL
      Unity College
      Wells PL
      Windham PL
      Witherle PL

## Slide 9: Scope of Analysis
In Scope:
  Circulating print monographs (pub or acq. 2003-2012)
  Juvenile titles (caveats)
  Special Collections (confirm?)
Out of Scope
  Monographs with existing MSCC commitments
  Serials (anything with record type ‘s’)
  Micro-formats/Fiche
  Government Documents
  Reference Books
  E-Books
  Music scores
  Lost/Withdrawn items
  Theses/Dissertations
  Maps

## Slide 10: Estimated Bib Record Totals
Library | No. of Monographs
Bangor Public | 55,200
Bates College | 98,900
Bowdoin College | 88,600
Colby College | 86,200
Maine State Library | 30,900
UMaine | 101,000
UMaine Augusta | 14,300
University of Southern Maine | 17,900
University of Maine at Machias | 3,700
University of Maine at Fort Kent | 9,800
University of Maine at Farmington | 13,600
University of Maine at Presque Isle | 2,800
Portland Public Library | 49,400
Minerva | 150,000
Totals | 722,300

## Slide 11: Scope of Analysis cont.…
Agree on strategy for excluding specific publishers
  Add to list
  Use Special Category flag?
  Exclude entirely from analysis?
Agree on strategy for excluding specific locations & subjects
  Use Special Category flag?
  Exclude entirely from analysis?
  Question for Colby, how to factor HathiTrust & EAST commitments?
Anything else related to scope?

## Slide 12: Project Outline
Libraries: Complete OCLC/SCS Cataloging & Data Questionnaire
SCS: Data validation & holdings lookups
SCS: Compile and Validate Individual Data Summaries
Libraries: Provide Bibliographic, Item, Circulation Data

## Slide 13: Project Outline cont.…
SCS: Compile data into GreenGlass/kick-off Collections & Operations Committee meeting to review
SCS: Allocate Retention Commitments
SCS: Reload GreenGlass Data to Reflect Retentions
Collections & Operations Committee: Meetings to experiment & agree on retention rules

## Slide 14: Project Outline cont.…
Libraries: Review Retention Proposals & rejected allocations reported to SCS
Load retention commitments into local ILS & WorldCat
Ongoing access to GreenGlass
SCS: GreenGlass reloaded with FINAL retention commitments

## Slide 15: Agree Timeline
Propose starting data questionnaires & submissions (January/February 2019)
Propose scheduling (even if we cancel some) weekly 1 hour virtual Collections & Operations Committee meetings to agree on retention rules (May-July 2019)
Retention commitment review (July-August)
Load agreed retention commitments into local ILSs & OCLC WorldCat (August-October)
Does this proposed schedule work?

## Slide 16: GreenGlass Demo
Take it away Cynthia!

## Slide 17: Next Steps
Arrange meeting with Minerva libraries – late summer 2018
UMaine billing non-Minerva libraries for analysis costs – September 2018
Send out data questionnaires to libraries – January 2019
Kickoff meeting – April/May 2019

## Slide 18: Other Business
  Transferring MSCC commitments
  Retention of Microfilm
  Accepting non-lending collections into MSCC
  EAST shared print summit
  OCLC Shared Print Registration Service